## Slide 1: Eastern Washington University Steering Committee Meeting
  June 21, 2024
Notes: Use for computer-screen presentations.

## Slide 2
  Finalized Guiding Principles
  Project update
  Roles & Responsibilities

## Slide 3: Guiding Principles Update

## Slide 4: Final Guiding Principles
A new budget model should:
Ensure the institution will be able to serve generations of students to come by aligning financial decisions with long-term planning.
Allow the institution to be responsive to external factors and to expand and contract as necessary.
Promote good stewardship of institutional resources by maintaining focus on strategic goals and objectives. Stewardship is the responsibility for managing institutional resources wisely and ensuring the contributions of each part are recognized while prioritizing the well-being of the institution as a whole.
Articulate the institutional trade-offs of resource allocation decisions.
Prioritize accountability by centering data-informed decisions and performance measurement as key drivers of resource management.
Foster trust by distributing resources in a predictable, consistent, collaborative, and transparent manner.

## Slide 5: Project Update

## Slide 6: Budget Revision Process
DISCOVER
Conduct an environmental scan of EWU’s current budget processes through document review, financial analysis, interviews and focus groups with employees and leadership.
DEVELOP
In collaboration with EWU, develop a revised budget model that includes an expenditure allocation model based on service unit production, performance, and institutional strategy.
COORDINATE
Develop a comprehensive project plan to address the scope of work, provide progress reports, and perform quality assurance.
REVIEW
Workshop the revised budget model with key EWU staff and stakeholders to promote transparency and change management.
ADOPT
Produce policies, procedures, trainings, and guides to support EWU in adopting the revised budget model.

## Slide 7: Project Milestones
Project Kickoff
Stakeholder Input
Interviews and Focus Groups
Current State Assessment Summarize strengths, weaknesses, and opportunities
Draft Budget model
Review Session Review and iterate on draft budget model with Moss Adams team, gathering additional information as needed
Review Session Review results of Discovery, and develop principles to guide budget model development
Stakeholder Input Review draft model with Moss Adams to provide input and additional considerations for implementation
Discovery Facilitation
Data, documents, interview set-up
Finalize Budget model
Execute
Carry out implementation of revised budget model
Implementation Support Develop policies, procedures, guides, trainings
FEB-APR
MAY-AUG
SEP-NOV
Moss Adams Deliverables
EWU Steering Committee
EWU Staff & Stakeholders

## Slide 8: Modeling Option 3 Performance-Based/Activity-Based/Incentive-Based Hybrid
Funding Source
Allocation Mechanism
Recipient
Capital
Auxiliaries
IDC contribution
Student credit hours rolling three-year avg
Designated unit
Designated unit
Auxiliaries
Capital
Support services
Internal services
IDC contribution
IDC contribution
IDC contribution
Grants and contracts
Designated fees
State operating
Tuition revenue
Undesignated fees
Academic college
Indirect cost allocation
Strategic initiatives
Performance measures

## Slide 9: Roles & Responsibilities

## Slide 10: Moss Adams
    Our scope of work includes the following:
      Conduct a review of Eastern Washington University’s (EWU or the University) current budgeting practices related to state operating processes, general student tuition, program-based tuition, and miscellaneous fees
      Research and benchmark industry best practices to identify innovative and effective budgeting approaches that are flexible over time
      Develop a flexible and responsive expenditure allocation model
      Assist in documenting the budget model through guidelines, policies, and procedures
      Provide training and change management support
Notes: Reiterate what we are and are not doing.
Not looking at role of UBC, roles and responsibilities, use of reserves, use of carryforward, salary savings treatment, efficiencies within individual functions, consideration of operating cost needs, fee assessments, etc. etc.

## Slide 11: Steering Committee
    According to the Charter:
      Provide diverse perspectives to inform new budget model development and define guiding principles
      Provide constructive feedback to refine and enhance the budget model throughout the design process to align with established guiding principles
      May recommend policy choices to Executive Leadership
      Provide regular status updates to campus to ensure stakeholders are informed throughout the process
      Foster understanding, ownership, and support for the budget model across the university community

## Slide 12: Executive Leadership
      Determines which budget model to explore
      Makes policy decisions that impact and inform the model
        Policy decisions may include allocation factors, percentages, incentives, performance measures, etc.
      Communicate the model to the campus community to enhance understanding and transparency
      Adopt the revised budget model
Notes: Reiterate what we are and are not doing.
Not looking at role of UBC, roles and responsibilities, use of reserves, use of carryforward, salary savings treatment, efficiencies within individual functions, consideration of operating cost needs, fee assessments, etc. etc.

## Slide 13: Key Decision Points
Decision | Moss Adams | Executive Team | Steering Committee | Campus Community
Determine budget model to explore | R | A | C | I
Design budget model | R | A | C | I
Identify policy decisions | R | A | C | I
Make policy decisions | R | A | C | I
Adopt the model | C | A, R | R | I
Communicate the model | C | A, R | R | I
R = Responsible (completes the work)
A = Accountable (set expectations, makes decisions)
C = Consulted (provide recommendations and feedback)
I = Informed (be looped in on progress)

## Slide 14: Next Steps
Moss Adams to begin workshopping budget model using EWU data
Upcoming Steering Committee work to focus on review of the draft budget model and identified policy decisions
Collaboratively continue to iterate upon the budget model

## Slide 15
Notes: NOTE: A version of the content disclaimer is available without the “Thank You” overlay if you prefer to show this at the beginning of your presentation,
-----
Presentation Builder path:
https://alliance.mossadams.com/proposalcentral/presentationbuilder/Forms/AllItems.aspx